## craig - project board
Craig - Project Board
Getting started
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Make sure you're all caught up from yesterday. |  | Craig Weinstein | Done | 2025-06-15 |  | 9402143998
Continue with today's tasks, according to the original plan. |  | Craig Weinstein | Done | 2025-06-15 |  | 9402144005
Double-check calendar dates |  | Craig Weinstein | Done | 2025-07-09 |  | 9552335970
|  |  |  | 2025-06-15 to 2025-07-09 | 0/3
Week 1
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Set up local development environment (Python 3.8+, Node.js 16+, PostgreSQL, Nginx, Gunicorn). Review Python fundamentals (e.g., scripting, libraries) and install IDE (VS Code) with Git for version control. Initialize Git repository and connect to GitHub. |  | Craig Weinstein | Working on it | 2025-07-07 |  | 9402144027
Create Django project and app using Python; Configure PostgreSQL database; introduce Django settings for security; install dependencies; HIPAA overview and encryption concepts |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9402144020
Explore JavaScript basics (e.g., variables, functions, DOM manipulation) as a front-end intro. Set up a simple React.js project with Create React App to understand components and state. |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533353045
Create initial database schema with migrations in Django/Python. Document setup process in README; discuss cybersecurity risks (e.g., data breaches) and mitigation (e.g., firewalls). |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533353664
|  |  |  | 2025-07-07 to 2025-07-17 | 0/4
Week 2
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Define RegulationUpdate and ChecklistItem models in Django/Python. Introduce encrypted fields using django-encrypted-model-fields for HIPAA compliance. |  | Craig Weinstein | Working on it | 2025-07-14 |  | 9533410624
Set up audit logging with django-auditlog in Python. Write SQL schema documentation; run migrations to create tables. |  | Craig Weinstein | Working on it | 2025-07-15 |  | 9533412253
Build on JavaScript: Implement a basic React.js component (e.g., simple login mock) to connect with Django. Test JavaScript API calls (e.g., fetch) to a placeholder Django endpoint. |  | Craig Weinstein | Working on it | 2025-07-16 |  | 9533415489
Test database connectivity and schema using pgAdmin or psql. Create a superuser; review cybersecurity basics: Authentication principles (e.g., JWT) and secure coding practices. |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533418359
|  |  |  | 2025-07-14 to 2025-07-17 | 0/4
Week 3
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Set up Django admin for RegulationUpdate and ChecklistItem models; add custom admin forms for manual entry. |  | Craig Weinstein | Working on it | 2025-07-21 |  | 9533437633
Test manual addition of sample regulations (simulate from HHS emails); create admin interface for reviewing updates. |  | Craig Weinstein |  | 2025-07-22 |  | 9533437674
Advance JavaScript/React: Integrate a simple React component with Django's admin or a test API. Explore React state management for future checklist features. |  | Craig Weinstein |  | 2025-07-23 |  | 9533437706
Test manual update process locally. Deepen cybersecurity: Study HIPAA Security Rule specifics (e.g., access controls) and apply to manual entry (e.g., encrypted fields). |  | Craig Weinstein |  | 2025-07-24 |  | 9533437761
|  |  |  | 2025-07-21 to 2025-07-24 | 0/4
Week 4
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Create serializers and viewsets for API endpoints in Django/Python. Implement JWT authentication with djangorestframework-simplejwt. |  | Craig Weinstein |  | 2025-07-28 |  | 9533446109
Restrict API access; use raw SQL for user-specific filtering in views. Test API endpoints using Postman. |  | Craig Weinstein |  | 2025-07-29 |  | 9533446182
Build on JavaScript/React: Create a basic checklist mock component in React.js. Connect React to Django API for data fetching. |  | Craig Weinstein |  | 2025-07-30 |  | 9533446233
Implement compliance report endpoint using raw SQL in Python. Document API; apply cybersecurity basics: Enable HTTPS in local Nginx and discuss audit logging. |  | Craig Weinstein |  | 2025-07-31 |  | 9533446317
|  |  |  | 2025-07-28 to 2025-07-31 | 0/4
Week 5
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Create React project (checklist-frontend) using Create React App. Install dependencies (axios, @mui /material, @emotion /react, @emotion /styled). |  | Craig Weinstein |  | 2025-08-04 |  | 9533452376
Develop Login component with username/password form and JWT integration. Configure axios for API requests with JWT headers. |  | Craig Weinstein |  | 2025-08-05 |  | 9533452418
Test login functionality against Django’s /api/token/ endpoint. Set up local storage for JWT token persistence. |  | Craig Weinstein |  | 2025-08-06 |  | 9533452454
Style Login component with Material-UI for responsive design. Document front-end setup and authentication flow. |  | Craig Weinstein |  | 2025-08-07 |  | 9533452495
|  |  |  | 2025-08-04 to 2025-08-07 | 0/4
Week 6
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Create Checklist component with a Material-UI table for regulations. Implement fields: regulation, description, completion checkbox, notes input, last updated. |  | Craig Weinstein |  | 2025-08-11 |  | 9533453611
Add API integration to fetch checklist items (GET /api/checklist/). Implement toggle functionality for completion status (PATCH /api/checklist/:id/). |  | Craig Weinstein |  | 2025-08-12 |  | 9533453688
Add notes input with real-time updates to the back-end. Implement in-app alerts for new regulation updates (GET /api/updates/). |  | Craig Weinstein |  | 2025-08-13 |  | 9533453759
Test checklist functionality (fetch, toggle, update notes). Ensure responsive design across devices. |  | Craig Weinstein |  | 2025-08-14 |  | 9533453860
|  |  |  | 2025-08-11 to 2025-08-14 | 0/4
Week 7
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Create ComplianceReport component with a Material-UI table. Display metrics: username, total items, completed items, completion percentage. |  | Craig Weinstein |  | 2025-08-18 |  | 9533455044
Integrate with /api/report/ endpoint to fetch report data. Test report rendering and data accuracy. |  | Craig Weinstein |  | 2025-08-19 |  | 9533455200
Add tabbed navigation in App.js to switch between Checklist and Compliance Report. Style report component for clarity and responsiveness. |  | Craig Weinstein |  | 2025-08-20 |  | 9533455391
Test tabbed navigation and report functionality. Document front-end components and API interactions. |  | Craig Weinstein |  | 2025-08-21 |  | 9533455498
|  |  |  | 2025-08-18 to 2025-08-21 | 0/4
Week 8
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Test end-to-end data flow: login → checklist → updates → report. Verify JWT authentication across all API calls. |  | Craig Weinstein |  | 2025-08-25 |  | 9533457008
Optimize API performance (e.g., reduce query load with SQL indexing). Add error handling in React for failed API requests. |  | Craig Weinstein |  | 2025-08-26 |  | 9533457096
Test HHS OCR scraping and checklist updates end-to-end. Ensure audit logs capture all changes (checklist updates, notes). |  | Craig Weinstein |  | 2025-08-27 |  | 9533457157
Document integration testing results. Prepare for deployment by updating API URLs for production. |  | Craig Weinstein |  | 2025-08-28 |  | 9533457240
|  |  |  | 2025-08-25 to 2025-08-28 | 0/4
Week 9
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Test API endpoints with Postman (CRUD operations, authentication). Verify SQL queries (ORM and raw) using pgAdmin or psql. |  | Craig Weinstein |  | 2025-09-01 |  | 9533487876
Test scraper reliability with different HHS OCR page structures. Optimize SQL queries (e.g., add indexes on user_id, regulation_update_id). |  | Craig Weinstein |  | 2025-09-02 |  | 9533488025
Test React components (login, checklist, report) with Jest. Verify responsive design on multiple devices (desktop, tablet). |  | Craig Weinstein |  | 2025-09-03 |  | 9533488166
Test audit logging for all database changes. Document test cases and results. |  | Craig Weinstein |  | 2025-09-04 |  | 9533488346
|  |  |  | 2025-09-01 to 2025-09-04 | 0/4
Week 10
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Install and configure Nginx as reverse proxy for local HTTPS (self-signed certs). |  | Craig Weinstein |  | 2025-09-08 |  | 9533490143
Set up Gunicorn to serve Django; configure PostgreSQL on local server with encryption. |  | Craig Weinstein |  | 2025-09-09 |  | 9533490299
Use crontab to schedule management commands (e.g., daily HHS OCR scraping). |  | Craig Weinstein |  | 2025-09-10 |  | 9533490530
Optional: Containerize app with Docker (compose files for Django, React, PostgreSQL); test local setup. |  | Craig Weinstein |  | 2025-09-11 |  | 9533490722
|  |  |  | 2025-09-08 to 2025-09-11 | 0/4
Week 11
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Deploy React front-end locally (e.g., via npm build, served by Nginx). |  | Craig Weinstein |  | 2025-09-15 |  | 9533493410
Integrate Django back-end with local PostgreSQL; test API connectivity. |  | Craig Weinstein |  | 2025-09-16 |  | 9533493526
Test end-to-end functionality: login, checklist, updates, reports on local network. |  | Craig Weinstein |  | 2025-09-17 |  | 9533493670
Verify scraper and update commands run via crontab; document local issues. |  | Craig Weinstein |  | 2025-09-18 |  | 9533493780
|  |  |  | 2025-09-15 to 2025-09-18 | 0/4
Week 12
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Verify encryption (notes, database) and physical security (e.g., firewall rules). |  | Craig Weinstein |  | 2025-09-22 |  | 9533495907
Conduct local security audit (OWASP ZAP); confirm HTTPS and JWT work. |  | Craig Weinstein |  | 2025-09-23 |  | 9533496016
Test with sample data; gather stakeholder feedback. |  | Craig Weinstein |  | 2025-09-24 |  | 9533496147
Finalize documentation (local setup, maintenance); plan for ongoing local updates. |  | Craig Weinstein |  | 2025-09-25 |  | 9533496280
|  |  |  | 2025-09-22 to 2025-09-25 | 0/4

## craig - project board-updates
Craig - Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9402144020 | Create Django project and app using Python; Configure PostgreSQL database; introduce Django settings for security; install dependencies; HIPAA overview and encryption concepts | Update |  | Craig Weinstein | 17/July/2025 04:23:11 PM | Here's a full descriptor for this particular day: * Create Django project (hipaa_checklist) and app (checklist) using Python. * Configure PostgreSQL database (hipaa_checklist); introduce Django settings for security (e.g., SECRET_KEY). * Install dependencies; cover cybersecurity basics: HIPAA overview (Privacy/Security Rules) and encryption concepts. | 0 |  | 4327982669
9402144027 | Set up local development environment (Python 3.8+, Node.js 16+, PostgreSQL, Nginx, Gunicorn). Review Python fundamentals (e.g., scripting, libraries) and install IDE (VS Code) with Git for version control. Initialize Git repository and connect to GitHub. | Update |  | Abhinav Piratla | 16/July/2025 11:11:39 AM | You’re currently shifting your job description and project scope, which means your course plan and project tasks will also change. Please update your project board to reflect the new courses, updated project goals, and revised deliverablesbased on the new plan we discussed. Let me know once it’s updated so we can review and realign the next steps. | 0 |  | 4323297653