## craig - project board
Craig - Project Board
Getting started
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Make sure you're all caught up from yesterday. |  | Craig Weinstein | Done | 2025-06-15 | v | 9402143998
Continue with today's tasks, according to the original plan. |  | Craig Weinstein | Done | 2025-06-15 | v | 9402144005
Double-check calendar dates |  | Craig Weinstein | Done | 2025-07-09 | v | 9552335970
|  |  |  | 2025-06-15 to 2025-07-09 | 3/3
Week 1
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Environment Setup and Git Init (Install tools, Python/Node/SQLite, VS Code/Git; start main.js vars/types). |  | Craig Weinstein | Working on it | 2025-07-07 |  | 9402144027
Django Project Creation and Security Settings (Create project/app, configure SQLite, HIPAA/encryption intro; add math/if to main.js). |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9402144020
JavaScript Basics and React Intro (Explore vars/functions/DOM; setup React app; connect main.js for output/logical ops). |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533353045
Create initial database schema with migrations in Django/Python. Document setup process in README; discuss cybersecurity risks (e.g., data breaches) and mitigation (e.g., firewalls). |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533353664
|  |  |  | 2025-07-07 to 2025-07-17 | 0/4
Week 2
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Define Models with Encryption (RegulationUpdate/ChecklistItem models; encrypted fields; add Zero Trust/Defense in Depth). |  | Craig Weinstein | Working on it | 2025-07-14 |  | 9533410624
Audit Logging and SQL Docs (Setup django-auditlog; schema docs/migrations; document supply chain/model in SOC_Fundamentals.docx). |  | Craig Weinstein | Working on it | 2025-07-15 |  | 9533412253
React Component and API Calls (Basic React login mock; JS API fetch; finalize main.js for all JS rubric). |  | Craig Weinstein | Working on it | 2025-07-16 |  | 9533415489
DB Connectivity Test and Cyber Basics (Test schema with sqlite3; superuser/auth review; complete cyber docs like IRP/Playbooks). |  | Craig Weinstein | Working on it | 2025-07-17 |  | 9533418359
|  |  |  | 2025-07-14 to 2025-07-17 | 0/4
Week 3
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Django Admin Setup for Models (Admin for RegulationUpdate/ChecklistItem; custom forms for manual HHS entry). |  | Craig Weinstein | Working on it | 2025-07-21 |  | 9533437633
Test Manual Regulation Addition (Simulate HHS email samples; admin review enhancements like filters). |  | Craig Weinstein | Working on it | 2025-07-22 |  | 9533437674
Advance React with API Integration (Connect React component to Django API; state management for checklists). |  | Craig Weinstein |  | 2025-07-23 |  | 9533437706
Manual Update Testing and HIPAA Deep Dive (Test add/update process; apply Security Rule to entry/encryption/logs). |  | Craig Weinstein |  | 2025-07-24 |  | 9533437761
|  |  |  | 2025-07-21 to 2025-07-24 | 0/4
Week 4
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
API Serializers and JWT Auth (Create serializers/viewsets; implement JWT for secure endpoints). |  | Craig Weinstein |  | 2025-07-28 |  | 9533446109
API Access Restrictions and Tests (User filtering with raw SQL; Postman testing for CRUD/auth). |  | Craig Weinstein |  | 2025-07-29 |  | 9533446182
React Checklist Mock and Data Fetch (Basic React component; connect to Django API for fetching). |  | Craig Weinstein |  | 2025-07-30 |  | 9533446233
Compliance Report Endpoint and Docs (Raw SQL report; document API; HTTPS/audit basics). |  | Craig Weinstein |  | 2025-07-31 |  | 9533446317
|  |  |  | 2025-07-28 to 2025-07-31 | 0/4
Week 5
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
React Project Dependencies Install (Create React app; add axios/MUI/emotion deps). |  | Craig Weinstein |  | 2025-08-04 |  | 9533452376
Login Component with JWT (Form for username/password; axios JWT headers config). |  | Craig Weinstein |  | 2025-08-05 |  | 9533452418
Login Testing and Token Storage (Test against /api/token/; local storage for persistence). |  | Craig Weinstein |  | 2025-08-06 |  | 9533452454
Style Login and Auth Flow Docs (MUI responsive design; document frontend/auth). |  | Craig Weinstein |  | 2025-08-07 |  | 9533452495
|  |  |  | 2025-08-04 to 2025-08-07 | 0/4
Week 6
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Checklist Table Component (MUI table for regulation fields: title, desc, checkbox, notes, updated). |  | Craig Weinstein |  | 2025-08-11 |  | 9533453611
Fetch and Toggle Integration (API GET /checklist/; PATCH for completion toggle). |  | Craig Weinstein |  | 2025-08-12 |  | 9533453688
Notes Updates and Alerts (Real-time notes PATCH; alerts for new updates via /api/updates/). |  | Craig Weinstein |  | 2025-08-13 |  | 9533453759
Checklist Functionality Testing (Fetch/toggle/notes tests; responsive design checks). |  | Craig Weinstein |  | 2025-08-14 |  | 9533453860
|  |  |  | 2025-08-11 to 2025-08-14 | 0/4
Week 7
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Compliance Report Table (MUI table for metrics: username, totals, completed, percentage). |  | Craig Weinstein |  | 2025-08-18 |  | 9533455044
Report Data Integration (API GET /api/report/; test rendering/accuracy). |  | Craig Weinstein |  | 2025-08-19 |  | 9533455200
Tabbed Navigation Addition (App.js tabs for Checklist/Report; style responsiveness). |  | Craig Weinstein |  | 2025-08-20 |  | 9533455391
Navigation and Component Docs (Test tabs/report; document frontend/API interactions). |  | Craig Weinstein |  | 2025-08-21 |  | 9533455498
|  |  |  | 2025-08-18 to 2025-08-21 | 0/4
Week 8
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
End-to-End Data Flow Testing (Login to checklist/updates/report; JWT verification). |  | Craig Weinstein |  | 2025-08-25 |  | 9533457008
API Optimization and Error Handling (SQL indexing; React error handling for APIs). |  | Craig Weinstein |  | 2025-08-26 |  | 9533457096
Manual Updates Integration Tests (End-to-end manual adds; audit logs for changes). |  | Craig Weinstein |  | 2025-08-27 |  | 9533457157
Document integration testing results. Prepare for deployment by updating API URLs for production. |  | Craig Weinstein |  | 2025-08-28 |  | 9533457240
|  |  |  | 2025-08-25 to 2025-08-28 | 0/4
Week 9
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
API CRUD and SQL Verification (Postman tests; query checks with sqlite3). |  | Craig Weinstein |  | 2025-09-01 |  | 9533487876
Manual Update Reliability Tests (Sample data tests; SQL query optimization). |  | Craig Weinstein |  | 2025-09-02 |  | 9533488025
React Component Jest Tests (Login/checklist/report; responsive device checks). |  | Craig Weinstein |  | 2025-09-03 |  | 9533488166
Audit Logging Tests and Docs (DB change logs; document cases/results). |  | Craig Weinstein |  | 2025-09-04 |  | 9533488346
|  |  |  | 2025-09-01 to 2025-09-04 | 0/4
Week 10
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Nginx Reverse Proxy Config (Local HTTPS with self-signed certs). |  | Craig Weinstein |  | 2025-09-08 |  | 9533490143
Waitress Django Server Setup (Serve app; SQLite file permissions/encryption). |  | Craig Weinstein |  | 2025-09-09 |  | 9533490299
Optional Docker Containerization (Compose for Django/React/SQLite; local tests). |  | Craig Weinstein |  | 2025-09-10 |  | 9533490530
Optional: Containerize app with Docker (compose files for Django, React, PostgreSQL); test local setup. |  | Craig Weinstein |  | 2025-09-11 |  | 9533490722
|  |  |  | 2025-09-08 to 2025-09-11 | 0/4
Week 11
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
React Local Deployment (npm build; serve via Nginx). |  | Craig Weinstein |  | 2025-09-15 |  | 9533493410
Backend SQLite API Connectivity (Integrate Django; test endpoints). |  | Craig Weinstein |  | 2025-09-16 |  | 9533493526
End-to-End Local Network Tests (Login/checklist/updates/reports functionality). |  | Craig Weinstein |  | 2025-09-17 |  | 9533493670
Manual Flow Verification and Docs (Test updates; document issues). |  | Craig Weinstein |  | 2025-09-18 |  | 9533493780
|  |  |  | 2025-09-15 to 2025-09-18 | 0/4
Week 12
Name | Subitems | Person | Status | Date | Verify | Item ID (auto generated)
Encryption and Security Verification (Notes/DB checks; firewall rules). |  | Craig Weinstein |  | 2025-09-22 |  | 9533495907
OWASP ZAP Security Audit (Local scan; confirm HTTPS/JWT). |  | Craig Weinstein |  | 2025-09-23 |  | 9533496016
Sample Data Testing and Feedback (Run with samples; gather input). |  | Craig Weinstein |  | 2025-09-24 |  | 9533496147
Final Docs and Maintenance Plan (Setup/maintenance; ongoing updates). |  | Craig Weinstein |  | 2025-09-25 |  | 9533496280
|  |  |  | 2025-09-22 to 2025-09-25 | 0/4

## craig - project board-updates
Craig - Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9402144020 | Django Project Creation and Security Settings (Create project/app, configure SQLite, HIPAA/encryption intro; add math/if to main.js). | Update |  | Craig Weinstein | 17/July/2025 04:23:11 PM | Here's a full descriptor for this particular day: * Create Django project (hipaa_checklist) and app (checklist) using Python. * Configure PostgreSQL database (hipaa_checklist); introduce Django settings for security (e.g., SECRET_KEY). * Install dependencies; cover cybersecurity basics: HIPAA overview (Privacy/Security Rules) and encryption concepts. | 0 |  | 4327982669
9402144020 | Django Project Creation and Security Settings (Create project/app, configure SQLite, HIPAA/encryption intro; add math/if to main.js). | Update |  | Craig Weinstein | 23/July/2025 01:45:38 PM | Create Django project (hipaa_checklist) and app (checklist) using Python. Configure SQLite database in settings.py; introduce Django settings for security (e.g., SECRET_KEY); install dependencies via requirements.txt; study HIPAA Privacy/Security Rules and encryption concepts. Update main.js with math operation and if/else for JS rubric. | 0 |  | 4342772754
9402144027 | Environment Setup and Git Init (Install tools, Python/Node/SQLite, VS Code/Git; start main.js vars/types). | Update |  | Abhinav Piratla | 16/July/2025 11:11:39 AM | You’re currently shifting your job description and project scope, which means your course plan and project tasks will also change. Please update your project board to reflect the new courses, updated project goals, and revised deliverablesbased on the new plan we discussed. Let me know once it’s updated so we can review and realign the next steps. | 0 |  | 4323297653
9402144027 | Environment Setup and Git Init (Install tools, Python/Node/SQLite, VS Code/Git; start main.js vars/types). | Update |  | Craig Weinstein | 23/July/2025 01:45:21 PM | Set up local development environment (Python 3.8+, Node.js 16+, SQLite via Django, Nginx, Waitress). Review Python fundamentals (e.g., scripting, libraries) and install IDE (VS Code) with Git for version control. Initialize Git repository and connect to GitHub. Start rubric prep: Create frontend/src/main.js as central JS file with basic variables and data types (e.g., int for score, string for name). | 0 |  | 4342771753
9533353045 | JavaScript Basics and React Intro (Explore vars/functions/DOM; setup React app; connect main.js for output/logical ops). | Update |  | Craig Weinstein | 23/July/2025 01:45:51 PM | Explore JavaScript basics (e.g., variables, functions, DOM manipulation) as a front-end intro. Set up a simple React.js project with Create React App to understand components and state. Connect main.js to App.js for interactive output (console/DOM, logical operator like AND) to fulfill JS rubric. | 0 |  | 4342773499
9533353664 | Create initial database schema with migrations in Django/Python. Document setup process in README; discuss cybersecurity risks (e.g., data breaches) and mitigation (e.g., firewalls). | Update |  | Craig Weinstein | 23/July/2025 01:46:02 PM | Create initial database schema with migrations in Django/Python (test with SQLite). Document setup process in README; discuss cybersecurity risks (e.g., data breaches) and mitigations (e.g., firewalls, encryption). Start cyber rubric: Draft docs/Policies.docx with 3 policy areas (access control, data protection, system use). | 0 |  | 4342774037
9533410624 | Define Models with Encryption (RegulationUpdate/ChecklistItem models; encrypted fields; add Zero Trust/Defense in Depth). | Update |  | Craig Weinstein | 23/July/2025 01:47:50 PM | Define RegulationUpdate and ChecklistItem models in Django/Python. Introduce encrypted fields using django-encrypted-model-fields for HIPAA compliance (e.g., notes field). Add Zero Trust (JWT in views.py) and Defense in Depth (3 layers: auth, encryption, logging) for cyber rubric. | 0 |  | 4342780043
9533412253 | Audit Logging and SQL Docs (Setup django-auditlog; schema docs/migrations; document supply chain/model in SOC_Fundamentals.docx). | Update |  | Craig Weinstein | 23/July/2025 01:48:03 PM | Set up audit logging with django-auditlog in Python. Write SQL schema documentation; run migrations to create tables in SQLite. Document supply chain security (e.g., verified dependencies) and advanced model (Bell-LaPadula for access) in docs/SOC_Fundamentals.docx. | 0 |  | 4342781755
9533415489 | React Component and API Calls (Basic React login mock; JS API fetch; finalize main.js for all JS rubric). | Update |  | Craig Weinstein | 23/July/2025 01:48:14 PM | Build on JavaScript: Implement a basic React.js component (e.g., simple login mock) to connect with Django. Test JavaScript API calls (e.g., fetch) to a placeholder Django endpoint. Finalize main.js with all JS rubric elements (interactive page, vars, types, math, if/else, logical op, outputs). | 0 |  | 4342782443
9533418359 | DB Connectivity Test and Cyber Basics (Test schema with sqlite3; superuser/auth review; complete cyber docs like IRP/Playbooks). | Update |  | Craig Weinstein | 23/July/2025 01:48:25 PM | Test database connectivity and schema using sqlite3 backend/db.sqlite3. Create a superuser; review cybersecurity basics: Authentication principles (e.g., JWT) and secure coding practices. Complete cyber rubric: Add IRP.docx (incident plan), Procedures.docx (docs), Playbooks.docx (scenarios), Knowledge_Base.docx (resources), SOC_Fundamentals.docx (SOC roles/monitoring). | 0 |  | 4342783010
9533437633 | Django Admin Setup for Models (Admin for RegulationUpdate/ChecklistItem; custom forms for manual HHS entry). | Update |  | Craig Weinstein | 23/July/2025 01:48:41 PM | Set up Django admin for RegulationUpdate and ChecklistItem models; add custom admin forms for manual entry of regulations from HHS emails. | 0 |  | 4342783901
9533437674 | Test Manual Regulation Addition (Simulate HHS email samples; admin review enhancements like filters). | Update |  | Craig Weinstein | 23/July/2025 01:48:54 PM | Test manual addition of sample regulations (simulate HHS email content, e.g., title, description, source URL); enhance admin interface for ease of review (e.g., list filters). | 0 |  | 4342784681
9533437706 | Advance React with API Integration (Connect React component to Django API; state management for checklists). | Update |  | Craig Weinstein | 23/July/2025 01:49:06 PM | Advance JavaScript/React: Integrate a simple React component with Django’s API to display regulations. Explore React state management for checklist features. Use main.js for any additional interactivity. | 0 |  | 4342785289
9533437761 | Manual Update Testing and HIPAA Deep Dive (Test add/update process; apply Security Rule to entry/encryption/logs). | Update |  | Craig Weinstein | 23/July/2025 01:49:15 PM | Test manual update process locally (add regulation, check user checklist). Deepen cybersecurity: Study HIPAA Security Rule specifics (e.g., access controls) and apply to manual entry (e.g., encrypted fields, audit logs). | 0 |  | 4342785749
9533446109 | API Serializers and JWT Auth (Create serializers/viewsets; implement JWT for secure endpoints). | Update |  | Craig Weinstein | 23/July/2025 01:49:30 PM | Create serializers and viewsets for API endpoints in Django/Python. Implement JWT authentication with djangorestframework-simplejwt. | 0 |  | 4342787426
9533446182 | API Access Restrictions and Tests (User filtering with raw SQL; Postman testing for CRUD/auth). | Update |  | Craig Weinstein | 23/July/2025 01:49:51 PM | Restrict API access; use raw SQL for user-specific filtering in views. Test API endpoints using Postman. | 0 |  | 4342791925
9533446233 | React Checklist Mock and Data Fetch (Basic React component; connect to Django API for fetching). | Update |  | Craig Weinstein | 23/July/2025 01:50:32 PM | Build on JavaScript/React: Create a basic checklist mock component in React.js. Connect React to Django API for data fetching. | 0 |  | 4342803909
9533446317 | Compliance Report Endpoint and Docs (Raw SQL report; document API; HTTPS/audit basics). | Update |  | Craig Weinstein | 23/July/2025 01:50:43 PM | Implement compliance report endpoint using raw SQL in Python. Document API; apply cybersecurity basics: Enable HTTPS in local Nginx and discuss audit logging. | 0 |  | 4342807738
9533452376 | React Project Dependencies Install (Create React app; add axios/MUI/emotion deps). | Update |  | Craig Weinstein | 23/July/2025 01:51:50 PM | Create React project (checklist-frontend) using Create React App. Install dependencies (axios, @mui/material, @emotion/react, @emotion/styled). | 0 |  | 4342817547
9533452418 | Login Component with JWT (Form for username/password; axios JWT headers config). | Update |  | Craig Weinstein | 23/July/2025 01:52:00 PM | Develop Login component with username/password form and JWT integration. Configure axios for API requests with JWT headers. | 0 |  | 4342818189
9533452454 | Login Testing and Token Storage (Test against /api/token/; local storage for persistence). | Update |  | Craig Weinstein | 23/July/2025 01:52:17 PM | Test login functionality against Django’s /api/token/ endpoint. Set up local storage for JWT token persistence. | 0 |  | 4342819189
9533452495 | Style Login and Auth Flow Docs (MUI responsive design; document frontend/auth). | Update |  | Craig Weinstein | 23/July/2025 01:52:28 PM | Style Login component with Material-UI for responsive design. Document front-end setup and authentication flow. | 0 |  | 4342819985
9533453611 | Checklist Table Component (MUI table for regulation fields: title, desc, checkbox, notes, updated). | Update |  | Craig Weinstein | 23/July/2025 01:52:40 PM | Create Checklist component with a Material-UI table for regulations. Implement fields: regulation, description, completion checkbox, notes input, last updated. | 0 |  | 4342821586
9533453688 | Fetch and Toggle Integration (API GET /checklist/; PATCH for completion toggle). | Update |  | Craig Weinstein | 23/July/2025 01:52:50 PM | Add API integration to fetch checklist items (GET /api/checklist/). Implement toggle functionality for completion status (PATCH /api/checklist/:id/). | 0 |  | 4342822623
9533453759 | Notes Updates and Alerts (Real-time notes PATCH; alerts for new updates via /api/updates/). | Update |  | Craig Weinstein | 23/July/2025 01:56:09 PM | Add notes input with real-time updates to the back-end. Implement in-app alerts for new regulation updates (GET /api/updates/). | 0 |  | 4342834528
9533453860 | Checklist Functionality Testing (Fetch/toggle/notes tests; responsive design checks). | Update |  | Craig Weinstein | 23/July/2025 01:56:17 PM | Test checklist functionality (fetch, toggle, update notes). Ensure responsive design across devices. | 0 |  | 4342835036
9533455044 | Compliance Report Table (MUI table for metrics: username, totals, completed, percentage). | Update |  | Craig Weinstein | 23/July/2025 01:56:28 PM | Create ComplianceReport component with a Material-UI table. Display metrics: username, total items, completed items, completion percentage. | 0 |  | 4342835577
9533455200 | Report Data Integration (API GET /api/report/; test rendering/accuracy). | Update |  | Craig Weinstein | 23/July/2025 01:56:35 PM | Integrate with /api/report/ endpoint to fetch report data. Test report rendering and data accuracy. | 0 |  | 4342835949
9533455391 | Tabbed Navigation Addition (App.js tabs for Checklist/Report; style responsiveness). | Update |  | Craig Weinstein | 23/July/2025 01:56:45 PM | Add tabbed navigation in App.js to switch between Checklist and Compliance Report. Style report component for clarity and responsiveness. | 0 |  | 4342836442
9533455498 | Navigation and Component Docs (Test tabs/report; document frontend/API interactions). | Update |  | Craig Weinstein | 23/July/2025 01:56:54 PM | Test tabbed navigation and report functionality. Document front-end components and API interactions. | 0 |  | 4342836919
9533457008 | End-to-End Data Flow Testing (Login to checklist/updates/report; JWT verification). | Update |  | Craig Weinstein | 23/July/2025 01:57:08 PM | Test end-to-end data flow: login → checklist → updates → report. Verify JWT authentication across all API calls. | 0 |  | 4342837605
9533457096 | API Optimization and Error Handling (SQL indexing; React error handling for APIs). | Update |  | Craig Weinstein | 23/July/2025 01:57:17 PM | Optimize API performance (e.g., reduce query load with SQL indexing). Add error handling in React for failed API requests. | 0 |  | 4342838159
9533457157 | Manual Updates Integration Tests (End-to-end manual adds; audit logs for changes). | Update |  | Craig Weinstein | 23/July/2025 01:57:32 PM | Test manual updates and checklist integrations end-to-end. Ensure audit logs capture all changes (checklist updates, notes). | 0 |  | 4342839149
9533457240 | Document integration testing results. Prepare for deployment by updating API URLs for production. | Update |  | Craig Weinstein | 23/July/2025 01:57:41 PM | Document integration testing results. Prepare for deployment by updating API URLs for production. | 0 |  | 4342839709
9533487876 | API CRUD and SQL Verification (Postman tests; query checks with sqlite3). | Update |  | Craig Weinstein | 23/July/2025 01:57:55 PM | Test API endpoints with Postman (CRUD operations, authentication). Verify SQL queries (ORM and raw) using sqlite3 command line. | 0 |  | 4342840520
9533488025 | Manual Update Reliability Tests (Sample data tests; SQL query optimization). | Update |  | Craig Weinstein | 23/July/2025 01:58:04 PM | Test manual update reliability with different sample data. Optimize SQL queries (e.g., add indexes on user_id, regulation_update_id). | 0 |  | 4342841035
9533488166 | React Component Jest Tests (Login/checklist/report; responsive device checks). | Update |  | Craig Weinstein | 23/July/2025 01:58:13 PM | Test React components (login, checklist, report) with Jest. Verify responsive design on multiple devices (desktop, tablet). | 0 |  | 4342841597
9533488346 | Audit Logging Tests and Docs (DB change logs; document cases/results). | Update |  | Craig Weinstein | 23/July/2025 01:58:25 PM | Test audit logging for all database changes. Document test cases and results. | 0 |  | 4342842640
9533490143 | Nginx Reverse Proxy Config (Local HTTPS with self-signed certs). | Update |  | Craig Weinstein | 23/July/2025 01:58:42 PM | Install and configure Nginx as reverse proxy for local HTTPS (self-signed certs). | 0 |  | 4342843673
9533490299 | Waitress Django Server Setup (Serve app; SQLite file permissions/encryption). | Update |  | Craig Weinstein | 23/July/2025 01:58:55 PM | Set up Waitress to serve Django; configure SQLite with encryption (file permissions). | 0 |  | 4342844372
9533490530 | Optional Docker Containerization (Compose for Django/React/SQLite; local tests). | Update |  | Craig Weinstein | 23/July/2025 01:59:05 PM | Optional: Containerize app with Docker (compose files for Django, React, SQLite); test local setup. | 0 |  | 4342844893
9533490722 | Optional: Containerize app with Docker (compose files for Django, React, PostgreSQL); test local setup. | Update |  | Craig Weinstein | 23/July/2025 01:59:15 PM | Integrate Wazuh for SIEM monitoring of logs; test basic policy enforcement tracking. | 0 |  | 4342845483
9533493410 | React Local Deployment (npm build; serve via Nginx). | Update |  | Craig Weinstein | 23/July/2025 01:59:27 PM | Deploy React front-end locally (e.g., via npm build, served by Nginx). | 0 |  | 4342846159
9533493526 | Backend SQLite API Connectivity (Integrate Django; test endpoints). | Update |  | Craig Weinstein | 23/July/2025 01:59:37 PM | Integrate Django back-end with local SQLite; test API connectivity. | 0 |  | 4342846730
9533493670 | End-to-End Local Network Tests (Login/checklist/updates/reports functionality). | Update |  | Craig Weinstein | 23/July/2025 01:59:59 PM | Test end-to-end functionality: login, checklist, updates, reports on local network. | 0 |  | 4342847999
9533493780 | Manual Flow Verification and Docs (Test updates; document issues). | Update |  | Craig Weinstein | 23/July/2025 02:00:07 PM | Verify manual update flows; document local issues. | 0 |  | 4342848747
9533495907 | Encryption and Security Verification (Notes/DB checks; firewall rules). | Update |  | Craig Weinstein | 23/July/2025 02:00:19 PM | Verify encryption (notes, database) and physical security (e.g., firewall rules). | 0 |  | 4342849677
9533496016 | OWASP ZAP Security Audit (Local scan; confirm HTTPS/JWT). | Update |  | Craig Weinstein | 23/July/2025 02:00:30 PM | Conduct local security audit (OWASP ZAP); confirm HTTPS and JWT work. | 0 |  | 4342850454
9533496147 | Sample Data Testing and Feedback (Run with samples; gather input). | Update |  | Craig Weinstein | 23/July/2025 02:00:40 PM | Test with sample data; gather stakeholder feedback. | 0 |  | 4342851275
9533496280 | Final Docs and Maintenance Plan (Setup/maintenance; ongoing updates). | Update |  | Craig Weinstein | 23/July/2025 02:00:54 PM | Finalize documentation (local setup, maintenance); plan for ongoing local updates. | 0 |  | 4342852430