## craig - project board
Craig - Project Board
Getting started
Name | Person | Status | Date
Make sure you're all caught up from yesterday. | Craig Weinstein | Working on it | 2025-06-15
Continue with today's tasks, according to the original plan. | Craig Weinstein | Done | 2025-06-15
See if you can't get ahead of the game, and do any of tomorrow's tasks today. | Craig Weinstein |  | 2025-06-16
2025-06-15 to 2025-06-16
Week 1
Name | Person | Status | Date
Networking Basics | Craig Weinstein | Working on it | 2025-07-08
Cybersecurity fundamentals | Craig Weinstein | Working on it | 2025-07-09
Try basic hacking exercises | Craig Weinstein | Working on it | 2025-07-10
Review key concepts from this week | Craig Weinstein | Working on it | 2025-07-11
2025-07-08 to 2025-07-11
Week 2
Name | Person | Status | Date
Splunk Fundamentals | Craig Weinstein | Working on it | 2025-07-15
Wireshark basics | Craig Weinstein | Working on it | 2025-07-16
MITRE ATT&CK basics | Craig Weinstein | Working on it | 2025-07-17
Recap and quiz yourself | Craig Weinstein | Working on it | 2025-07-18
2025-07-15 to 2025-07-18
Week 3
Name | Person | Status | Date
Study 7 major incidents | Craig Weinstein | Working on it | 2025-07-22
Learn key cybersecurity concepts | Craig Weinstein | Working on it | 2025-07-23
MITRE mapping practice | Craig Weinstein | Working on it | 2025-07-24
Create cheat sheet | Craig Weinstein | Working on it | 2025-07-25
2025-07-22 to 2025-07-25
Week 4
Name | Person | Status | Date
VM & lab setup | Craig Weinstein | Working on it | 2025-07-29
Install ELK stack | Craig Weinstein | Working on it | 2025-07-30
Install Zeek & Velociraptor | Craig Weinstein | Working on it | 2025-07-31
Test log ingestion | Craig Weinstein | Working on it | 2025-08-01
2025-07-29 to 2025-08-01
Week 5
Name | Person | Status | Date
Write detection rules (failed login) | Craig Weinstein | Working on it | 2025-08-05
Write rule for PowerShell abuse | Craig Weinstein | Working on it | 2025-08-06
Test in ELK | Craig Weinstein | Working on it | 2025-08-07
Visualize rules in Kibana | Craig Weinstein | Working on it | 2025-08-08
2025-08-05 to 2025-08-08
Week 6
Name | Person | Status | Date
Refine Filebeat/Sysmon config | Craig Weinstein | Working on it | 2025-08-12
Add GeoIP enrichment | Craig Weinstein | Working on it | 2025-08-13
Kibana dashboard setup | Craig Weinstein | Working on it | 2025-08-14
SIEM data validation | Craig Weinstein | Working on it | 2025-08-15
2025-08-12 to 2025-08-15
Week 7
Name | Person | Status | Date
Simulate brute-force attack | Craig Weinstein | Working on it | 2025-08-19
Detect w/ SIEM & triage | Craig Weinstein | Working on it | 2025-08-20
Simulate PowerShell abuse | Craig Weinstein | Working on it | 2025-08-21
Reduce false positives | Craig Weinstein | Working on it | 2025-08-22
2025-08-19 to 2025-08-22
Week 8
Name | Person | Status | Date
Simulate C2/file dropper | Craig Weinstein | Working on it | 2025-08-26
Investigate logs + WireShark | Craig Weinstein | Working on it | 2025-08-27
Draft incident report | Craig Weinstein | Working on it | 2025-08-28
Map to MITRE | Craig Weinstein | Working on it | 2025-08-29
2025-08-26 to 2025-08-29
Week 9
Name | Person | Status | Date
Review detection rules | Craig Weinstein | Working on it | 2025-09-02
Close visibility gaps | Craig Weinstein | Working on it | 2025-09-03
Organize screenshots & logs | Craig Weinstein | Working on it | 2025-09-04
Draft second report | Craig Weinstein | Working on it | 2025-09-05
2025-09-02 to 2025-09-05
Week 10
Name | Person | Status | Date
Polish incident reports | Craig Weinstein | Working on it | 2025-09-09
Compile IOC table | Craig Weinstein | Working on it | 2025-09-10
Write alert summary | Craig Weinstein | Working on it | 2025-09-11
Document response steps | Craig Weinstein | Working on it | 2025-09-12
2025-09-09 to 2025-09-12
Week 11
Name | Person | Status | Date
Create and improve GitHub repo | Craig Weinstein | Working on it | 2025-09-16
Write README with setup | Craig Weinstein | Working on it | 2025-09-17
Add screenshots + alerts | Craig Weinstein | Working on it | 2025-09-18
Organize directory structure | Craig Weinstein | Working on it | 2025-09-19
2025-09-16 to 2025-09-19
Week 12
Name | Person | Status | Date
Record walkthrough video | Craig Weinstein | Working on it | 2025-09-23
Write project case study | Craig Weinstein | Working on it | 2025-09-24
Submit to portfolio | Craig Weinstein | Working on it | 2025-09-25
Present to class (and, optionally, Post to LinkedIn) | Craig Weinstein | Working on it | 2025-09-26
2025-09-23 to 2025-09-26